{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["Sheet1"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":259,"n_cols":21,"rows_kept":259,"flags":["formulas_cached_only"]}
["Facility Management Software System"]
["Transaction Totals by Location"]
["Park:   CABR"]
["Asset Code:   Not Selected"]
["Facility Type:   Not Selected"]
["Location:   Not Selected"]
["Transaction Start Date:   from  10/01/2012  to  \"No Upper Bound\""]
["Work Type:   Not Selected"]
["Sub Work Type:   Not Selected"]
["Status:   Not Selected"]
["PMIS#:   Not Selected"]
["Group By:  Location"]
["Format:   Excel"]
["FMSS Database:   FMSS Production"]
["Transaction Totals by Location.rpt"]
["Data as of  08/22/2013 15:32 PM"]
["The Report Should be Exported In Excel Format"]
[]
["WO#","Description","Work Type","Sub Work Type","Status","PMIS#","PMIS Comp","Location","Description","Asset Code","Facility Type","OB","DM","Est Lab Hrs","Est Lab Cost","Act Lab Hrs","Act Lab Cost","Act Mat Cost","Act Tool Cost","Act Serv Cost","Total Act Cost"]
["12263345","Install Temporary Solar Ballard Lights at Visitor Center Parking Lots.","FM","CM","COMP",null,null,"102682","Visitor Center Parking","1300","1310","2",{"v":370823.75,"d":"$370,824"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":4.5,"d":"4.50"},{"v":122.85,"d":"$123"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":122.85,"d":"$123"}]
["11963423","CHECK DRAINS AND DROP INLETS PM, Visitor Center Parking","FM","PM","COMP",null,null,"102682","Visitor Center Parking","1300","1310","2",{"v":370823.75,"d":"$370,824"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.24,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.24,"d":"$13"}]
["12158096","FY13 CABR Repair Regulatory/Directional Signs","FM","RM","APPR",null,null,"102682","Visitor Center Parking","1300","1310","2",{"v":370823.75,"d":"$370,824"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},1.75,{"v":46.7,"d":"$47"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":46.7,"d":"$47"}]
["11159232","FY13 CABR Visitor Center Parking Grounds","FO","GC","APPR",null,null,"102682","Visitor Center Parking","1300","1310","2",{"v":370823.75,"d":"$370,824"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":82,"d":"82.00"},{"v":2095.61,"d":"$2,096"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":2095.61,"d":"$2,096"}]
["11159392","FY13 CABR Visitor Center Parking Weed Control","FO","PC","APPR",null,null,"102682","Visitor Center Parking","1300","1310","2",{"v":370823.75,"d":"$370,824"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":2,"d":"2.00"},{"v":51.25,"d":"$51"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":51.25,"d":"$51"}]
["11725366","Fill Hole in Asphalt in Ocean View Parking Lot","FM","CM","COMP",null,null,"102686","Ocean View Parking","1300","1310","2",{"v":3387.69,"d":"$3,388"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":3.5,"d":"3.50"},{"v":97.83,"d":"$98"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":97.83,"d":"$98"}]
["11159239","FY13 CABR Ocean View Parking Grounds","FO","GC","APPR",null,null,"102686","Ocean View Parking","1300","1310","2",{"v":3387.69,"d":"$3,388"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},71.25,{"v":1816.14,"d":"$1,816"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1816.14,"d":"$1,816"}]
["11159403","FY13 CABR Ocean View Parking  Weed Control","FO","PC","APPR",null,null,"102686","Ocean View Parking","1300","1310","2",{"v":3387.69,"d":"$3,388"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["11159246","FY13 CABR Tidepool Parking Grounds","FO","GC","APPR",null,null,"102698","Tidepool Parking Lot","1300","1310","2",{"v":1059505.45,"d":"$1,059,505"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":60,"d":"60.00"},{"v":1533.66,"d":"$1,534"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1533.66,"d":"$1,534"}]
["11159253","FY13 CABR Coast View Parking Grounds","FO","GC","APPR",null,null,"102699","Coast View Parking","1300","1310","3",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":47.5,"d":"47.50"},{"v":1216.66,"d":"$1,217"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1216.66,"d":"$1,217"}]
["11159260","FY13 CABR Sea Cove Parking Grounds","FO","GC","APPR",null,null,"102700","Sea Cove Parking","1300","1310","3",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},46.25,{"v":1179.98,"d":"$1,180"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1179.98,"d":"$1,180"}]
["11724151","Pump Drop Inlet","FM","CM","COMP",null,null,"102701","Cabrillo Memorial Drive","1100","1110","2",{"v":126827.15,"d":"$126,827"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":2.5,"d":"2.50"},{"v":69.88,"d":"$70"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":69.88,"d":"$70"}]
["11963440","CHECK DRAINS AND DROP INLETS PM, Cabrillo Memorial Drive","FM","PM","COMP",null,null,"102701","Cabrillo Memorial Drive","1100","1110","2",{"v":126827.15,"d":"$126,827"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.24,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.24,"d":"$13"}]
["11159211","FY13 CABR Cabrillo Memorial Drive Grounds","FO","GC","APPR",null,null,"102701","Cabrillo Memorial Drive","1100","1110","2",{"v":126827.15,"d":"$126,827"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":48.5,"d":"48.50"},{"v":1241.19,"d":"$1,241"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1241.19,"d":"$1,241"}]
["11159423","FY13 CABR  Lighthouse Service Road  Weed Control","FO","PC","APPR",null,null,"102702","Lighthouse Service Road","1100","1110","3",{"v":98579.01,"d":"$98,579"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.5,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.5,"d":"$7"}]
["11963406","CHECK DRAINS AND DROP INLETS PM, Battery Humphreys Road","FM","PM","COMP",null,null,"102703","Battery Humphreys Road","1100","1110","3",{"v":77733.21,"d":"$77,733"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.24,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.24,"d":"$13"}]
["13441320","CHECK DRAINS AND DROP INLETS PM, Battery Humphreys Road","FM","PM","COMP",null,null,"102703","Battery Humphreys Road","1100","1110","3",{"v":77733.21,"d":"$77,733"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.25,"d":"$6"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.25,"d":"$6"}]
["11341798","FY13 CABR Historic Structures Maintenance Searchlight Shelter #19","FM","CM","APPR",null,null,"108820","Searchlight Shelter #19","7300","7340","3",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":26,"d":"$26"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":26,"d":"$26"}]
["13211988","RINSE EXTERIOR METALWORK PM , Searchlight #19","FM","PM","COMP",null,null,"108820","Searchlight Shelter #19","7300","7340","3",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":3,"d":"3.00"},{"v":80.93,"d":"$81"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":80.93,"d":"$81"}]
["13002408","Repair Battery Humphreys Hatch Cover Lid","FM","DM","APPR",null,null,"108822","Battery Humphreys","7300","7340","3",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":13,"d":"13.00"},{"v":363.36,"d":"$363"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":363.36,"d":"$363"}]
["13003151","Repair Batteries Woodward and Grant Hatch Cover Lid","FM","DM","APPR",null,null,"108823","Battery Woodward and Grant, Base -End Station","7300","7340","3",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},11.75,{"v":328.43,"d":"$328"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":328.43,"d":"$328"}]
["11341791","FY13 CABR Historic Structures Maintenance Searchlight Shelter #15","FM","CM","APPR",null,null,"108824","Searchlight Shelter #15","7300","7340","2",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["12550946","Searchlight #15 Hatch Project","FM","CM","APPR",null,null,"108824","Searchlight Shelter #15","7300","7340","2",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":29,"d":"29.00"},{"v":804.65,"d":"$805"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":804.65,"d":"$805"}]
["13211978","RINSE EXTERIOR METALWORK PM , Searchlight #15","FM","PM","COMP",null,null,"108824","Searchlight Shelter #15","7300","7340","2",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":2.5,"d":"2.50"},{"v":69.88,"d":"$70"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":69.88,"d":"$70"}]
["11159573","FY13 CABR Battery Point Loma Panama Gun Mounts Weed Control","FO","PC","APPR",null,null,"108829","Battery Point Loma Panama Gun Mounts","7300","7340","2",{"v":1000,"d":"$1,000"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1.5,"d":"1.50"},{"v":39,"d":"$39"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":39,"d":"$39"}]
["11963389","CHECK DRAINS AND DROP INLETS PM, Cabrillo Road","FM","PM","COMP",null,null,"109730","Cabrillo Road","1100","1110","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.24,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.24,"d":"$13"}]
["11159487","FY13 CABR Cabrillo Road Grounds","FO","GC","APPR",null,null,"109730","Cabrillo Road","1100","1110","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},17.75,{"v":466.01,"d":"$466"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":466.01,"d":"$466"}]
["13294057","Gatchell Rd. Post and Rail Fence Repair Project","FM","CM","APPR",null,null,"109731","Gatchell Road","1100","1110","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},25.75,{"v":657,"d":"$657"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":657,"d":"$657"}]
["11153873","CHECK DRAINS AND DROP INLETS PM, Gatchell Road","FM","PM","COMP",null,null,"109731","Gatchell Road","1100","1110","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},1.25,{"v":32.5,"d":"$33"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":32.5,"d":"$33"}]
["11395749","CHECK DRAINS AND DROP INLETS PM, Gatchell Road","FM","PM","COMP",null,null,"109731","Gatchell Road","1100","1110","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":27.95,"d":"$28"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":27.95,"d":"$28"}]
["12282385","CHECK DRAINS AND DROP INLETS PM, Gatchell Road","FM","PM","COMP",null,null,"109731","Gatchell Road","1100","1110","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":27.95,"d":"$28"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":27.95,"d":"$28"}]
["12712012","CHECK DRAINS AND DROP INLETS PM, Gatchell Road","FM","PM","COMP",null,null,"109731","Gatchell Road","1100","1110","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":2,"d":"2.00"},{"v":52.95,"d":"$53"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":52.95,"d":"$53"}]
["13211950","CHECK DRAINS AND DROP INLETS PM, Gatchell Road","FM","PM","COMP",null,null,"109731","Gatchell Road","1100","1110","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":26,"d":"$26"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":26,"d":"$26"}]
["11159494","FY13 CABR Gatchell Road Grounds","FO","GC","APPR",null,null,"109731","Gatchell Road","1100","1110","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":10,"d":"10.00"},{"v":260.68,"d":"$261"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":260.68,"d":"$261"}]
["12488514","WATERBAR, STEP, SURFACE REPAIR PM, Coast View Parking to Tidepools Trail","FM","PM","COMP",null,null,"109732","Coast View Parking to Tidepools Trail","2100","2120","3",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":3,"d":"3.00"},{"v":83.85,"d":"$84"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":83.85,"d":"$84"}]
["12488513","WATERBAR, STEP, SURFACE REPAIR PM, Military History to Wedding Bluff Trail","FM","PM","COMP",null,null,"109733","Military History to Wedding Bluff Trail","2100","2120","3",{"v":32103.94,"d":"$32,104"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1.5,"d":"1.50"},{"v":41.93,"d":"$42"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":41.93,"d":"$42"}]
["11159550","FY13 CABR Military History to Wedding Bluff Trail Grounds","FO","GC","APPR",null,null,"109733","Military History to Wedding Bluff Trail","2100","2120","3",{"v":32103.94,"d":"$32,104"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},4.75,{"v":130.55,"d":"$131"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":130.55,"d":"$131"}]
["12488515","WATERBAR, STEP, SURFACE REPAIR PM, Tidepool Parking Lot to Tidepool Overlook Trail","FM","PM","COMP",null,null,"109734","Tidepool Parking Lot to Tidepool Overlook Trail","2100","2120","2",{"v":3387.69,"d":"$3,388"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1.5,"d":"1.50"},{"v":41.93,"d":"$42"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":41.93,"d":"$42"}]
["12992968","ROOF AND GUTTERS PM , Visitor Contact Building","FM","PM","COMP",null,null,"109735","Visitor Contact Building","4100","4110","3",{"v":3104.98,"d":"$3,105"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["12993079","FIRE PROTECTION SYSTEM, WET PIPE PM, Visitor Contact Building","FM","PM","COMP",null,null,"109735","Visitor Contact Building","4100","4110","3",{"v":3104.98,"d":"$3,105"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.99,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.99,"d":"$7"}]
["13441288","FAN, ROOF/WALL EXHAUST PM , Visitor Contact Building","FM","PM","COMP",null,null,"109735","Visitor Contact Building","4100","4110","3",{"v":3104.98,"d":"$3,105"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.99,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.99,"d":"$7"}]
["11159267","FY13 CABR Visitor Contact Building Custodial","FO","CU","APPR",null,null,"109735","Visitor Contact Building","4100","4110","3",{"v":3104.98,"d":"$3,105"},{"v":10,"d":"10.00"},{"v":250,"d":"$250"},{"v":45,"d":"45.00"},{"v":1158.1100000000001,"d":"$1,158"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1158.1100000000001,"d":"$1,158"}]
["11159630","FY13 CABR Visitor Contact Building Grounds","FO","GC","APPR",null,null,"109735","Visitor Contact Building","4100","4110","3",{"v":3104.98,"d":"$3,105"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["11342303","SHOP POWER TOOL PM","FM","PM","COMP",null,null,"109736","Upper Maintenance Shop","4100","4160","5",{"v":6035.22,"d":"$6,035"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":26,"d":"$26"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":26,"d":"$26"}]
["11963492","SHOP POWER TOOL PM","FM","PM","COMP",null,null,"109736","Upper Maintenance Shop","4100","4160","5",{"v":6035.22,"d":"$6,035"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["12488518","SHOP POWER TOOL PM","FM","PM","COMP",null,null,"109736","Upper Maintenance Shop","4100","4160","5",{"v":6035.22,"d":"$6,035"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":27.95,"d":"$28"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":27.95,"d":"$28"}]
["12992932","ROOF AND GUTTERS PM , Upper Maintenance Shop","FM","PM","COMP",null,null,"109736","Upper Maintenance Shop","4100","4160","5",{"v":6035.22,"d":"$6,035"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["11159511","FY13 CABR Shop Cleanup Custodial","FO","CU","APPR",null,null,"109736","Upper Maintenance Shop","4100","4160","5",{"v":6035.22,"d":"$6,035"},{"v":10,"d":"10.00"},{"v":250,"d":"$250"},12.75,{"v":338.75,"d":"$339"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":338.75,"d":"$339"}]
["12711978","ROOF AND GUTTERS PM , Pumphouse","FM","PM","COMP",null,null,"109737","Pumphouse","4100","4150","5",{"v":2823.07,"d":"$2,823"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["13484521","8\" Water Main Break Support","FO","MG","APPR",null,null,"109737","Pumphouse","4100","4150","5",{"v":2823.07,"d":"$2,823"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":3.5,"d":"3.50"},{"v":97.83,"d":"$98"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":97.83,"d":"$98"}]
["12711958","PHOTOVOLTIC SYSTEM PM, Lower Maintenance Building","FM","PM","COMP",null,null,"109743","Photo Voltaic System, Lower Maintenance","5400","5420","4",{"v":1000,"d":"$1,000"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["11159348","FY13 CABR Kelp Forest Primary Custodial","FO","CU","APPR",null,null,"233967","Kelp Forest Overlook: Primary Structure","4100","4129",null,{"v":0,"d":"$0"},{"v":10,"d":"10.00"},{"v":250,"d":"$250"},{"v":45,"d":"45.00"},{"v":1152.97,"d":"$1,153"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1152.97,"d":"$1,153"}]
["11159356","FY13 CABR Kelp Forest Secondary Custodial","FO","CU","APPR",null,null,"233968","Kelp Forest Overlook: Secondary Structure","4100","4129",null,{"v":0,"d":"$0"},{"v":10,"d":"10.00"},{"v":250,"d":"$250"},{"v":43.5,"d":"43.50"},{"v":1110.72,"d":"$1,111"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1110.72,"d":"$1,111"}]
["11725381","Fill Hole in Asphalt in Lighthouse Parking Lot","FM","CM","COMP",null,null,"234528","Lighthouse Parking Area","1300","1310",null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":2,"d":"2.00"},{"v":55.9,"d":"$56"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":55.9,"d":"$56"}]
["11131992","FY13 CABR Facility Maintenance Tidepool Vault Toilet","FM","CM","APPR",null,null,"239606","Tidepool Parking Lot Restroom","4100","4124",null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["13406269","RINSE EXTERIOR SURFACES PM , Vault Toilet","FM","PM","COMP",null,null,"239606","Tidepool Parking Lot Restroom","4100","4124",null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":4,"d":"4.00"},{"v":105.9,"d":"$106"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":105.9,"d":"$106"}]
["11159610","FY13 CABR Tidepool Parking Lot Restroom Custodial","FO","CU","APPR",null,null,"239606","Tidepool Parking Lot Restroom","4100","4124",null,{"v":0,"d":"$0"},{"v":10,"d":"10.00"},{"v":250,"d":"$250"},225.25,{"v":5768,"d":"$5,768"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":5768,"d":"$5,768"}]
["11159618","FY13 CABR Pumping Vault Restroom","FO","CU","APPR",null,null,"239606","Tidepool Parking Lot Restroom","4100","4124",null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},6.25,{"v":171.77,"d":"$172"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":171.77,"d":"$172"}]
["11131971","FY13 CABR Facility Maintenance Administration Building","FM","CM","APPR",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},11.25,{"v":303.23,"d":"$303"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":303.23,"d":"$303"}]
["11131993","FY13 CABR Facility Maintenance Administration Building Plumbing","FM","CM","APPR",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},4.75,{"v":120.23,"d":"$120"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":120.23,"d":"$120"}]
["12274131","Retrofit CNMF office Ceiling Lights.","FM","CR","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},13.25,{"v":351.33,"d":"$351"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":351.33,"d":"$351"}]
["12347213","Install New Fluorescent Light Len's","FM","CR","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},12.25,{"v":331.18,"d":"$331"},{"v":218.4,"d":"$218"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":549.58,"d":"$550"}]
["11153890","VACUUM CLEANER PM","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":25,"d":"$25"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":25,"d":"$25"}]
["11153915","PORTABLE GENERATOR PM","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.5,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.5,"d":"$7"}]
["11342302","VACUUM CLEANER PM","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},1.25,{"v":31.25,"d":"$31"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":31.25,"d":"$31"}]
["11342347","PORTABLE GENERATOR PM","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["11395766","VACUUM CLEANER PM","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},1.25,{"v":31.25,"d":"$31"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":31.25,"d":"$31"}]
["11395791","PORTABLE GENERATOR PM","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["11963343","ROOF AND GUTTERS PM , Administration Building","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["11963491","VACUUM CLEANER PM","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":25,"d":"$25"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":25,"d":"$25"}]
["11963535","PORTABLE GENERATOR PM","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["12282370","WAX AND POLISH FLOORS  PM , Administration Building","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":5,"d":"5.00"},{"v":128.5,"d":"$129"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":128.5,"d":"$129"}]
["12282441","PORTABLE GENERATOR PM","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["12712030","VACUUM CLEANER PM","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":12.5,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":12.5,"d":"$13"}]
["12712066","PORTABLE GENERATOR PM","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.5,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.5,"d":"$7"}]
["12993231","VACUUM CLEANER PM","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":25,"d":"$25"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":25,"d":"$25"}]
["12993283","PORTABLE GENERATOR PM","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.5,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.5,"d":"$7"}]
["13211923","WATER HEATER PM, Administration Building","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0.633333333333333,"d":"0.63"},{"v":12.67,"d":"$13"},0.25,{"v":6.99,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.99,"d":"$7"}]
["13211977","VACUUM CLEANER PM","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":25,"d":"$25"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":25,"d":"$25"}]
["13212008","PORTABLE GENERATOR PM","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["13441298","PANELBOARD, 400 AMPS PM , Administration Building","FM","PM","COMP",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":0.433333333333333,"d":"0.43"},{"v":8.67,"d":"$9"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["11159146","FY13 CABR Administration Building Custodial","FO","CU","APPR",null,null,"71929","Administration Building","4100","4110","3",{"v":46412.1,"d":"$46,412"},{"v":10,"d":"10.00"},{"v":250,"d":"$250"},{"v":166.5,"d":"166.50"},{"v":4254.25,"d":"$4,254"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":4254.25,"d":"$4,254"}]
["11131978","FY13 CABR Facility Maintenance Assistant Keepers Quarters","FM","CM","APPR",null,null,"71932","Assistant Keepers Quarters","4100","4129","1",{"v":18222.57,"d":"$18,223"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":27.95,"d":"$28"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":27.95,"d":"$28"}]
["10137738","WAX AND POLISH FLOORS  PM , Assistant Keepers Quarters","FM","PM","COMP",null,null,"71932","Assistant Keepers Quarters","4100","4129","1",{"v":18222.57,"d":"$18,223"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1.5,"d":"1.50"},{"v":37.5,"d":"$38"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":37.5,"d":"$38"}]
["11395636","FIRE PROTECTION SYSTEM, WET PIPE","FM","PM","COMP",null,null,"71932","Assistant Keepers Quarters","4100","4129","1",{"v":18222.57,"d":"$18,223"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":27.96,"d":"$28"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":27.96,"d":"$28"}]
["11963217","FIRE PROTECTION SYSTEM, WET PIPE","FM","PM","COMP",null,null,"71932","Assistant Keepers Quarters","4100","4129","1",{"v":18222.57,"d":"$18,223"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["12282294","FIRE PROTECTION SYSTEM, WET PIPE","FM","PM","COMP",null,null,"71932","Assistant Keepers Quarters","4100","4129","1",{"v":18222.57,"d":"$18,223"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["12282372","WAX AND POLISH FLOORS  PM , Assistant Keepers Quarters","FM","PM","COMP",null,null,"71932","Assistant Keepers Quarters","4100","4129","1",{"v":18222.57,"d":"$18,223"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":4.5,"d":"4.50"},{"v":115.5,"d":"$116"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":115.5,"d":"$116"}]
["12487708","FIRE PROTECTION SYSTEM, WET PIPE","FM","PM","COMP",null,null,"71932","Assistant Keepers Quarters","4100","4129","1",{"v":18222.57,"d":"$18,223"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.99,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.99,"d":"$7"}]
["12992771","FIRE PROTECTION SYSTEM, WET PIPE","FM","PM","COMP",null,null,"71932","Assistant Keepers Quarters","4100","4129","1",{"v":18222.57,"d":"$18,223"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.99,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.99,"d":"$7"}]
["12992956","ROOF AND GUTTERS PM , Assistant Keepers Quarters","FM","PM","COMP",null,null,"71932","Assistant Keepers Quarters","4100","4129","1",{"v":18222.57,"d":"$18,223"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["11159195","FY13 CABR Assistant Keeper's Quarters Custodial","FO","CU","APPR",null,null,"71932","Assistant Keepers Quarters","4100","4129","1",{"v":18222.57,"d":"$18,223"},{"v":10,"d":"10.00"},{"v":250,"d":"$250"},150.75,{"v":3849.34,"d":"$3,849"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":3849.34,"d":"$3,849"}]
["11159128","FY13 CABR Assistant Keeper's Quarters Grounds","FO","GC","APPR",null,null,"71932","Assistant Keepers Quarters","4100","4129","1",{"v":18222.57,"d":"$18,223"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":55,"d":"55.00"},{"v":1398.49,"d":"$1,398"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1398.49,"d":"$1,398"}]
["11131980","FY13 CABR Facility Maintenance Ballast View Rest Area","FM","CM","APPR",null,null,"71936","Ballast View Rest Area","3100","3110","3",{"v":53265.58,"d":"$53,266"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1.5,"d":"1.50"},{"v":41.93,"d":"$42"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":41.93,"d":"$42"}]
["12712044","PRESSURE WASH BRICK PM , Ballast View Rest Area","FM","PM","COMP",null,null,"71936","Ballast View Rest Area","3100","3110","3",{"v":53265.58,"d":"$53,266"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":3,"d":"3.00"},{"v":76.5,"d":"$77"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":76.5,"d":"$77"}]
["11159275","FY13 CABR Ballast View Rest Area Grounds","FO","GC","APPR",null,null,"71936","Ballast View Rest Area","3100","3110","3",{"v":53265.58,"d":"$53,266"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},50.25,{"v":1291.55,"d":"$1,292"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1291.55,"d":"$1,292"}]
["12488516","WATERBAR, STEP, SURFACE REPAIR PM, Bayside Trail","FM","PM","COMP",null,null,"71937","Bayside Trail","2100","2130","4",{"v":720761,"d":"$720,761"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":27.95,"d":"$28"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":27.95,"d":"$28"}]
["11159385","FY13 CABR Bayside Trail Grounds","FO","GC","APPR",null,null,"71937","Bayside Trail","2100","2130","4",{"v":720761,"d":"$720,761"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":54,"d":"54.00"},{"v":1380.5,"d":"$1,381"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1380.5,"d":"$1,381"}]
["11159480","FY13 CABR Cabrillo Statue Grounds","FO","GC","APPR",null,null,"71938","Cabrillo Statue","7100","7120","3",{"v":1262.72,"d":"$1,263"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":41.5,"d":"41.50"},{"v":1060,"d":"$1,060"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1060,"d":"$1,060"}]
["11131984","FY13 CABR Facility Maintenance Entrance Station","FM","CM","APPR",null,null,"71941","Entrance Station","4100","4110","4",{"v":1007.06,"d":"$1,007"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":4,"d":"4.00"},{"v":111.81,"d":"$112"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":111.81,"d":"$112"}]
["10137855","WAX AND POLISH FLOORS  PM , Entrance Station","FM","PM","COMP",null,null,"71941","Entrance Station","4100","4110","4",{"v":1007.06,"d":"$1,007"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":25.5,"d":"$26"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":25.5,"d":"$26"}]
["11963367","AIR HANDLING UNIT PM, Entrance Station","FM","PM","COMP",null,null,"71941","Entrance Station","4100","4110","4",{"v":1007.06,"d":"$1,007"},{"v":0.416666666666667,"d":"0.42"},{"v":8.790000000000001,"d":"$9"},0.25,{"v":6.5,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.5,"d":"$7"}]
["12282384","WAX AND POLISH FLOORS  PM , Entrance Station","FM","PM","COMP",null,null,"71941","Entrance Station","4100","4110","4",{"v":1007.06,"d":"$1,007"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"}]
["12711990","ROOF AND GUTTERS PM , Entrance Station","FM","PM","COMP",null,null,"71941","Entrance Station","4100","4110","4",{"v":1007.06,"d":"$1,007"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.5,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.5,"d":"$7"}]
["12712002","AIR HANDLING UNIT PM, Entrance Station","FM","PM","COMP",null,null,"71941","Entrance Station","4100","4110","4",{"v":1007.06,"d":"$1,007"},{"v":0.416666666666667,"d":"0.42"},{"v":8.790000000000001,"d":"$9"},0.25,{"v":6.5,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.5,"d":"$7"}]
["13211941","WATER HEATER PM, Entrance Station","FM","PM","COMP",null,null,"71941","Entrance Station","4100","4110","4",{"v":1007.06,"d":"$1,007"},{"v":0.633333333333333,"d":"0.63"},{"v":12.67,"d":"$13"},0.25,{"v":6.99,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.99,"d":"$7"}]
["11159602","FY13 CABR Entrance Station Grounds","FO","GC","APPR",null,null,"71941","Entrance Station","4100","4110","4",{"v":1007.06,"d":"$1,007"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":7,"d":"7.00"},{"v":185.33,"d":"$185"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":185.33,"d":"$185"}]
["11884486","Installation of Electrical Hand Dryers","CI","NC","COMP",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},28.25,{"v":783.74,"d":"$784"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":783.74,"d":"$784"}]
["11131973","FY13 CABR Facility Maintenance Exhibit Room & Auditorium","FM","CM","APPR",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":10.5,"d":"10.50"},{"v":285.66,"d":"$286"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":285.66,"d":"$286"}]
["11131974","FY13 CABR Facility Maintenance Exhibit Room & Auditorium Plumbing","FM","CM","APPR",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":5.5,"d":"5.50"},{"v":150.81,"d":"$151"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":150.81,"d":"$151"}]
["10137739","SCRUB FLOORS AND SPOT CLEAN CARPETS  PM , Exhibit Room & Auditorium","FM","PM","COMP",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["11342267","DOOR, SLIDING, ELECTRIC PM, Exhibit Room","FM","PM","COMP",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":1.2166666666666701,"d":"1.22"},{"v":25.66,"d":"$26"},0.25,{"v":6.5,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.5,"d":"$7"}]
["11395731","AUDITORIUM HVAC PM: FILTERS","FM","PM","COMP",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.75,{"v":20.96,"d":"$21"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":20.96,"d":"$21"}]
["11963276","AUDITORIUM HVAC PM: FILTERS","FM","PM","COMP",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["11963319","ROOF AND GUTTERS PM , Exhibit Room & Auditorium","FM","PM","COMP",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":27.95,"d":"$28"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":27.95,"d":"$28"}]
["12282204","AIR HANDLING UNIT, 3 TONS TO 24 TONS","FM","PM","COMP",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":0.416666666666667,"d":"0.42"},{"v":8.790000000000001,"d":"$9"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["12282353","AUDITORIUM HVAC PM: FILTERS","FM","PM","COMP",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["12282373","SCRUB FLOORS AND SPOT CLEAN CARPETS  PM , Exhibit Room & Auditorium","FM","PM","COMP",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":5.5,"d":"5.50"},{"v":140,"d":"$140"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":140,"d":"$140"}]
["12487826","AUDITORIUM HVAC PM: FILTERS","FM","PM","COMP",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["12711923","AUDITORIUM HVAC PM: FILTERS","FM","PM","COMP",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["12711934","DOOR, SLIDING, ELECTRIC PM, Exhibit Room","FM","PM","COMP",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":1.2166666666666701,"d":"1.22"},{"v":25.66,"d":"$26"},0.75,{"v":20.96,"d":"$21"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":20.96,"d":"$21"}]
["12992555","AIR HANDLING UNIT, 3 TONS TO 24 TONS","FM","PM","COMP",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":0.416666666666667,"d":"0.42"},{"v":8.790000000000001,"d":"$9"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["12992830","AUDITORIUM HVAC PM: FILTERS","FM","PM","COMP",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["13211913","AUDITORIUM HVAC PM: FILTERS","FM","PM","COMP",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.75,{"v":20.96,"d":"$21"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":20.96,"d":"$21"}]
["11159138","FY13 CABR Aud/Exhibit and Restrooms Custodial","FO","CU","APPR",null,null,"71945","Exhibit Room & Auditorium","4100","4129","2",{"v":111923.2,"d":"$111,923"},{"v":10,"d":"10.00"},{"v":250,"d":"$250"},{"v":500,"d":"500.00"},{"v":12728.01,"d":"$12,728"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":12728.01,"d":"$12,728"}]
["12992920","ROOF AND GUTTERS PM , Greenhouse","FM","PM","COMP",null,null,"71951","Greenhouse","4100","4180","4",{"v":1515.26,"d":"$1,515"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.75,{"v":20.96,"d":"$21"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":20.96,"d":"$21"}]
["11131977","FY13 CABR Facility Maintenance Lighthouse","FM","CM","APPR",null,null,"71952","Lighthouse","4100","4173","1",{"v":51884.76,"d":"$51,885"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1.5,"d":"1.50"},{"v":41.93,"d":"$42"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":41.93,"d":"$42"}]
["11963377","ROOF AND GUTTERS PM , Lighthouse","FM","PM","COMP",null,null,"71952","Lighthouse","4100","4173","1",{"v":51884.76,"d":"$51,885"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["13211967","RINSE EXTERIOR METALWORK PM , Lighthouse","FM","PM","COMP",null,null,"71952","Lighthouse","4100","4173","1",{"v":51884.76,"d":"$51,885"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1.5,"d":"1.50"},{"v":41.93,"d":"$42"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":41.93,"d":"$42"}]
["11159203","FY13 CABR Lighthouse Custodial","FO","CU","APPR",null,null,"71952","Lighthouse","4100","4173","1",{"v":51884.76,"d":"$51,885"},{"v":10,"d":"10.00"},{"v":250,"d":"$250"},{"v":157.5,"d":"157.50"},{"v":4027.75,"d":"$4,028"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":4027.75,"d":"$4,028"}]
["11131976","FY13 CABR Facility Maintenance Lighthouse Comfort Station","FM","CM","APPR",null,null,"71953","Lighthouse Comfort Station","4100","4124","2",{"v":17882.09,"d":"$17,882"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1.5,"d":"1.50"},{"v":39,"d":"$39"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":39,"d":"$39"}]
["10187562","WATERLESS URINAL PM (LHCS)","FM","PM","CLOSE",null,null,"71953","Lighthouse Comfort Station","4100","4124","2",{"v":17882.09,"d":"$17,882"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["11342304","WATERLESS URINAL PM (LHCS)","FM","PM","COMP",null,null,"71953","Lighthouse Comfort Station","4100","4124","2",{"v":17882.09,"d":"$17,882"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.5,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.5,"d":"$7"}]
["11963307","ROOF AND GUTTERS PM , Lighthouse Comfort Station,","FM","PM","COMP",null,null,"71953","Lighthouse Comfort Station","4100","4124","2",{"v":17882.09,"d":"$17,882"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["11963493","WATERLESS URINAL PM (LHCS)","FM","PM","COMP",null,null,"71953","Lighthouse Comfort Station","4100","4124","2",{"v":17882.09,"d":"$17,882"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.5,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.5,"d":"$7"}]
["12282443","SCRUB FLOORS PM, Lighthouse Comfort Station","FM","PM","COMP",null,null,"71953","Lighthouse Comfort Station","4100","4124","2",{"v":17882.09,"d":"$17,882"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":2,"d":"2.00"},{"v":50,"d":"$50"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":50,"d":"$50"}]
["12488520","WATERLESS URINAL PM (LHCS)","FM","PM","COMP",null,null,"71953","Lighthouse Comfort Station","4100","4124","2",{"v":17882.09,"d":"$17,882"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["12993245","WATERLESS URINAL PM (LHCS)","FM","PM","COMP",null,null,"71953","Lighthouse Comfort Station","4100","4124","2",{"v":17882.09,"d":"$17,882"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.75,{"v":19.5,"d":"$20"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":19.5,"d":"$20"}]
["13441408","WATERLESS URINAL PM (LHCS)","FM","PM","COMP",null,null,"71953","Lighthouse Comfort Station","4100","4124","2",{"v":17882.09,"d":"$17,882"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["11159178","FY13 CABR Lighthouse Comfort Station Custodial","FO","CU","APPR",null,null,"71953","Lighthouse Comfort Station","4100","4124","2",{"v":17882.09,"d":"$17,882"},{"v":10,"d":"10.00"},{"v":250,"d":"$250"},{"v":173,"d":"173.00"},{"v":4440.38,"d":"$4,440"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":4440.38,"d":"$4,440"}]
["11159526","FY13 CABR Lighthouse Comfort Station Grounds","FO","GC","APPR",null,null,"71953","Lighthouse Comfort Station","4100","4124","2",{"v":17882.09,"d":"$17,882"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":49.5,"d":"49.50"},{"v":1259,"d":"$1,259"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1259,"d":"$1,259"}]
["11131979","FY13 CABR Facility Maintenance Lower Maintenance Building","FM","CM","APPR",null,null,"71954","Lower Maintenance Building","4100","4141","4",{"v":29618.73,"d":"$29,619"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":6,"d":"6.00"},{"v":167.71,"d":"$168"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":167.71,"d":"$168"}]
["12735412","Replace Glass in Metal Window Lower Maintenance Building","FM","DM","APPR",null,null,"71954","Lower Maintenance Building","4100","4141","4",{"v":29618.73,"d":"$29,619"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},38.75,{"v":1022.61,"d":"$1,023"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1022.61,"d":"$1,023"}]
["11153856","DOOR, OVERHEAD, MANUAL PM, Lower Maintenance Building","FM","PM","COMP",null,null,"71954","Lower Maintenance Building","4100","4141","4",{"v":29618.73,"d":"$29,619"},{"v":1.1,"d":"1.10"},{"v":13.94,"d":"$14"},0.75,{"v":19.5,"d":"$20"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":19.5,"d":"$20"}]
["11963289","DOOR, OVERHEAD, MANUAL PM, Lower Maintenance Building","FM","PM","COMP",null,null,"71954","Lower Maintenance Building","4100","4141","4",{"v":29618.73,"d":"$29,619"},{"v":1.1,"d":"1.10"},{"v":13.94,"d":"$14"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["11963295","ROOF AND GUTTERS PM, Lower Maintenance Building","FM","PM","COMP",null,null,"71954","Lower Maintenance Building","4100","4141","4",{"v":29618.73,"d":"$29,619"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["12711952","DOOR, OVERHEAD, MANUAL PM, Lower Maintenance Building","FM","PM","COMP",null,null,"71954","Lower Maintenance Building","4100","4141","4",{"v":29618.73,"d":"$29,619"},{"v":1.1,"d":"1.10"},{"v":13.94,"d":"$14"},0.75,{"v":19.5,"d":"$20"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":19.5,"d":"$20"}]
["13211932","WATER HEATER PM, Lower Maintenance Building","FM","PM","COMP",null,null,"71954","Lower Maintenance Building","4100","4141","4",{"v":29618.73,"d":"$29,619"},{"v":0.633333333333333,"d":"0.63"},{"v":12.67,"d":"$13"},0.25,{"v":6.99,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.99,"d":"$7"}]
["11159170","FY13 CABR Lower Maintenance Building Custodial","FO","CU","APPR",null,null,"71954","Lower Maintenance Building","4100","4141","4",{"v":29618.73,"d":"$29,619"},{"v":10,"d":"10.00"},{"v":250,"d":"$250"},58.25,{"v":1497.66,"d":"$1,498"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1497.66,"d":"$1,498"}]
["11159473","FY13 CABR Lower Maintenance Building Grounds","FO","GC","APPR",null,null,"71954","Lower Maintenance Building","4100","4141","4",{"v":29618.73,"d":"$29,619"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},33.25,{"v":852.65,"d":"$853"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":852.65,"d":"$853"}]
["11726230","Install Straw Wattles at Lighthouse Comfort Station","FM","CM","COMP",null,null,"71955","Managed Landscape (Lighthouse)","3100","3110","2",{"v":1750,"d":"$1,750"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},3.25,{"v":89.37,"d":"$89"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":89.37,"d":"$89"}]
["10187580","GUM REMOVAL PM, Managed Landscape (Lighthouse)","FM","PM","COMP",null,null,"71955","Managed Landscape (Lighthouse)","3100","3110","2",{"v":1750,"d":"$1,750"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":12.5,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":12.5,"d":"$13"}]
["11963474","CHECK DRAINS AND DROP INLETS PM, Managed Landscape (Lighthouse)","FM","PM","COMP",null,null,"71955","Managed Landscape (Lighthouse)","3100","3110","2",{"v":1750,"d":"$1,750"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.24,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.24,"d":"$13"}]
["12488538","GUM REMOVAL PM, Managed Landscape (Lighthouse)","FM","PM","COMP",null,null,"71955","Managed Landscape (Lighthouse)","3100","3110","2",{"v":1750,"d":"$1,750"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["13441389","CHECK DRAINS AND DROP INLETS PM, Managed Landscape (Lighthouse)","FM","PM","COMP",null,null,"71955","Managed Landscape (Lighthouse)","3100","3110","2",{"v":1750,"d":"$1,750"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.25,"d":"$6"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.25,"d":"$6"}]
["11159378","FY13 CABR Managed Landscape (Lighthouse) Grounds","FO","GC","APPR",null,null,"71955","Managed Landscape (Lighthouse)","3100","3110","2",{"v":1750,"d":"$1,750"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":84.5,"d":"84.50"},{"v":2157.46,"d":"$2,157"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":2157.46,"d":"$2,157"}]
["11159516","FY13 CABR  Maintained Landscape, Lighthouse,  Weed Control","FO","PC","APPR",null,null,"71955","Managed Landscape (Lighthouse)","3100","3110","2",{"v":1750,"d":"$1,750"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1.5,"d":"1.50"},{"v":39,"d":"$39"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":39,"d":"$39"}]
["11153917","SEWAGE LIFT STATION PM","FM","PM","COMP",null,null,"71956","Lift Station","5200","5210","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.75,{"v":19.5,"d":"$20"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":19.5,"d":"$20"}]
["11395804","SEWAGE LIFT STATION PM","FM","PM","COMP",null,null,"71956","Lift Station","5200","5210","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1.5,"d":"1.50"},{"v":41.93,"d":"$42"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":41.93,"d":"$42"}]
["11963548","SEWAGE LIFT STATION PM","FM","PM","COMP",null,null,"71956","Lift Station","5200","5210","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":26,"d":"$26"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":26,"d":"$26"}]
["12488562","SEWAGE LIFT STATION PM","FM","PM","COMP",null,null,"71956","Lift Station","5200","5210","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":27.95,"d":"$28"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":27.95,"d":"$28"}]
["12712079","SEWAGE LIFT STATION PM","FM","PM","COMP",null,null,"71956","Lift Station","5200","5210","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":27.95,"d":"$28"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":27.95,"d":"$28"}]
["12993341","SEWAGE LIFT STATION PM","FM","PM","COMP",null,null,"71956","Lift Station","5200","5210","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":27.95,"d":"$28"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":27.95,"d":"$28"}]
["13212033","SEWAGE LIFT STATION PM","FM","PM","COMP",null,null,"71956","Lift Station","5200","5210","4",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.75,{"v":20.96,"d":"$21"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":20.96,"d":"$21"}]
["11159364","FY13 CABR Managed Landscape (Tidepool Area) Grounds","FO","GC","APPR",null,null,"71958","Managed Landscape (Tidepool Area)","3100","3110","3",{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},17.25,{"v":447.47,"d":"$447"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":447.47,"d":"$447"}]
["12347242","Install New/Repair 2' High Wooden Fence Along Breezeway","CI","NC","APPR",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},40.25,{"v":1087.85,"d":"$1,088"},{"v":133.68,"d":"$134"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1221.5299999999997,"d":"$1,222"}]
["11721163","Install Poles and Pennants for Centennial","FM","CM","APPR",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},7.25,{"v":198.95,"d":"$199"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":198.95,"d":"$199"}]
["10187423","GUM REMOVAL PM, Managed Landscape (Visitor Center)","FM","PM","COMP",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":12.5,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":12.5,"d":"$13"}]
["10187595","BLOWER EQUIPMENT PM","FM","PM","CLOSE",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.75,{"v":19.5,"d":"$20"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":19.5,"d":"$20"}]
["10187617","POWER HEDGE TRIMMERS PM","FM","PM","COMP",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":26,"d":"$26"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":26,"d":"$26"}]
["10188235","POWER HEDGE TRIMMERS PM","FM","PM","COMP",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["11153905","BLOWER EQUIPMENT PM","FM","PM","COMP",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.5,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.5,"d":"$7"}]
["11395781","BLOWER EQUIPMENT PM","FM","PM","COMP",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["11395793","POWER HEDGE TRIMMERS PM","FM","PM","COMP",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["11963525","BLOWER EQUIPMENT PM","FM","PM","COMP",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["11963537","POWER HEDGE TRIMMERS PM","FM","PM","COMP",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["12488519","GUM REMOVAL PM, Managed Landscape (Visitor Center)","FM","PM","COMP",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["12712056","BLOWER EQUIPMENT PM","FM","PM","COMP",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.5,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.5,"d":"$7"}]
["12712068","POWER HEDGE TRIMMERS PM","FM","PM","COMP",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["12993307","POWER HEDGE TRIMMERS PM","FM","PM","COMP",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["13211998","BLOWER EQUIPMENT PM","FM","PM","COMP",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.5,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.5,"d":"$7"}]
["13212011","POWER HEDGE TRIMMERS PM","FM","PM","COMP",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.75,{"v":19.5,"d":"$20"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":19.5,"d":"$20"}]
["12158093","FY13 CABR Repair Park Irrigation","FM","RM","APPR",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":14,"d":"14.00"},{"v":391.3,"d":"$391"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":391.3,"d":"$391"}]
["11159371","FY13 CABR Managed Landscape (Visitor Center) Grounds","FO","GC","APPR",null,null,"71964","Managed Landscape (Visitor Center)","3100","3110","2",{"v":9302.92,"d":"$9,303"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},18.25,{"v":474.4,"d":"$474"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":474.4,"d":"$474"}]
["11131981","FY13 CABR Facility Maintenance Military History Building","FM","CM","APPR",null,null,"71965","Military History Building","4100","4129","1",{"v":3337.64,"d":"$3,338"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":3,"d":"3.00"},{"v":81.9,"d":"$82"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":81.9,"d":"$82"}]
["10137737","WAX AND POLISH FLOORS PM , Military History Building","FM","PM","COMP",null,null,"71965","Military History Building","4100","4129","1",{"v":3337.64,"d":"$3,338"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},3.25,{"v":83,"d":"$83"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":83,"d":"$83"}]
["11963355","ROOF AND GUTTERS PM , Military History Building","FM","PM","COMP",null,null,"71965","Military History Building","4100","4129","1",{"v":3337.64,"d":"$3,338"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["12282371","WAX AND POLISH FLOORS PM , Military History Building","FM","PM","COMP",null,null,"71965","Military History Building","4100","4129","1",{"v":3337.64,"d":"$3,338"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":6,"d":"6.00"},{"v":154.5,"d":"$155"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":154.5,"d":"$155"}]
["11159162","FY13 CABR Military History Exhibit Custodial","FO","CU","APPR",null,null,"71965","Military History Building","4100","4129","1",{"v":3337.64,"d":"$3,338"},{"v":10,"d":"10.00"},{"v":250,"d":"$250"},{"v":126.5,"d":"126.50"},{"v":3218.37,"d":"$3,218"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":3218.37,"d":"$3,218"}]
["11159466","FY13 CABR Military History Building Grounds","FO","GC","APPR",null,null,"71965","Military History Building","4100","4129","1",{"v":3337.64,"d":"$3,338"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},1.75,{"v":44.25,"d":"$44"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":44.25,"d":"$44"}]
["11754597","Install Fan Motor in Condensing Unit","FM","CM","COMP",null,null,"71974","Museum Storage","4100","4141","1",{"v":3980.85,"d":"$3,981"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":5.5,"d":"5.50"},{"v":153.73,"d":"$154"},{"v":79.98,"d":"$80"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":233.71,"d":"$234"}]
["11963158","FIRE PROTECTION SYSTEM, WET PIPE","FM","PM","COMP",null,null,"71974","Museum Storage","4100","4141","1",{"v":3980.85,"d":"$3,981"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["12282194","AIR HANDLING UNIT, 3 TONS TO 24 TONS","FM","PM","COMP",null,null,"71974","Museum Storage","4100","4141","1",{"v":3980.85,"d":"$3,981"},{"v":0.416666666666667,"d":"0.42"},{"v":8.790000000000001,"d":"$9"},0.25,{"v":6.99,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.99,"d":"$7"}]
["12282214","HEAT PUMP, AIR COOLED, UP TO 5 TONS","FM","PM","COMP",null,null,"71974","Museum Storage","4100","4141","1",{"v":3980.85,"d":"$3,981"},{"v":0.666666666666667,"d":"0.67"},{"v":14.06,"d":"$14"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["12282226","COND UNIT, AIR COOLED, 3-24 TONS (With Compressor)","FM","PM","COMP",null,null,"71974","Museum Storage","4100","4141","1",{"v":3980.85,"d":"$3,981"},{"v":0.383333333333333,"d":"0.38"},{"v":8.08,"d":"$8"},0.25,{"v":6.99,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.99,"d":"$7"}]
["12282235","FIRE PROTECTION SYSTEM, WET PIPE","FM","PM","COMP",null,null,"71974","Museum Storage","4100","4141","1",{"v":3980.85,"d":"$3,981"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["12487590","FIRE PROTECTION SYSTEM, WET PIPE","FM","PM","COMP",null,null,"71974","Museum Storage","4100","4141","1",{"v":3980.85,"d":"$3,981"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.99,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.99,"d":"$7"}]
["12992652","FIRE PROTECTION SYSTEM, WET PIPE","FM","PM","COMP",null,null,"71974","Museum Storage","4100","4141","1",{"v":3980.85,"d":"$3,981"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},0.25,{"v":6.99,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.99,"d":"$7"}]
["12992944","ROOF AND GUTTERS PM , Museum Storage","FM","PM","COMP",null,null,"71974","Museum Storage","4100","4141","1",{"v":3980.85,"d":"$3,981"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["11131985","FY13 CABR Facility Maintenance Paved Sidewalks","FM","CM","APPR",null,null,"71978","Paved Sidewalks","2100","2150","4",{"v":98659,"d":"$98,659"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1.5,"d":"1.50"},{"v":40.95,"d":"$41"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":40.95,"d":"$41"}]
["12158091","FY13 CABR Repair Post and Rope","FM","RM","APPR",null,null,"71978","Paved Sidewalks","2100","2150","4",{"v":98659,"d":"$98,659"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":19.5,"d":"19.50"},{"v":514.7,"d":"$515"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":514.7,"d":"$515"}]
["12158092","FY13 CABR Repair Pathway Lights","FM","RM","APPR",null,null,"71978","Paved Sidewalks","2100","2150","4",{"v":98659,"d":"$98,659"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":7,"d":"7.00"},{"v":192.73,"d":"$193"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":192.73,"d":"$193"}]
["12158095","FY13 CABR Repaint/Repair Interpretive Signs","FM","RM","APPR",null,null,"71978","Paved Sidewalks","2100","2150","4",{"v":98659,"d":"$98,659"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},8.75,{"v":234.33,"d":"$234"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":234.33,"d":"$234"}]
["12158143","FY13 CABR Replace Slats in Benches","FM","RM","APPR",null,null,"71978","Paved Sidewalks","2100","2150","4",{"v":98659,"d":"$98,659"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":6,"d":"6.00"},{"v":167.7,"d":"$168"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":167.7,"d":"$168"}]
["11159456","FY13 CABR  Paved Sidewalks  Weed Control","FO","PC","APPR",null,null,"71978","Paved Sidewalks","2100","2150","4",{"v":98659,"d":"$98,659"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13,"d":"$13"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13,"d":"$13"}]
["12711968","PHOTOVOLTIC SYSTEM PM, VC Breezeway","FM","PM","COMP",null,null,"71979","Photovoltaic System VC Breezeway","5400","5420","4",{"v":1000,"d":"$1,000"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0.5,"d":"0.50"},{"v":13.98,"d":"$14"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":13.98,"d":"$14"}]
["12620214","Visitor Center View Building Exterior Receptacles Project","CI","AL","APPR",null,null,"71983","Visitor Center View Bldg","4100","4129","1",{"v":105230.93,"d":"$105,231"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":2,"d":"2.00"},{"v":55.9,"d":"$56"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":55.9,"d":"$56"}]
["12620265","Visitor Center View Building Exterior Lighting Project","CI","AL","APPR",null,null,"71983","Visitor Center View Bldg","4100","4129","1",{"v":105230.93,"d":"$105,231"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":5.5,"d":"5.50"},{"v":153.72,"d":"$154"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":153.72,"d":"$154"}]
["11131972","FY13 CABR Facility Maintenance Visitor Center View Bldg","FM","CM","APPR",null,null,"71983","Visitor Center View Bldg","4100","4129","1",{"v":105230.93,"d":"$105,231"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1.5,"d":"1.50"},{"v":41.93,"d":"$42"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":41.93,"d":"$42"}]
["11342277","DOOR, SLIDING, ELECTRIC PM, Visitor Center View Bldg","FM","PM","COMP",null,null,"71983","Visitor Center View Bldg","4100","4129","1",{"v":105230.93,"d":"$105,231"},{"v":1.2166666666666701,"d":"1.22"},{"v":25.66,"d":"$26"},0.25,{"v":6.5,"d":"$7"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6.5,"d":"$7"}]
["11963331","ROOF AND GUTTERS PM , Visitor Center View Bldg","FM","PM","COMP",null,null,"71983","Visitor Center View Bldg","4100","4129","1",{"v":105230.93,"d":"$105,231"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1,"d":"1.00"},{"v":27.95,"d":"$28"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":27.95,"d":"$28"}]
["12711943","DOOR, SLIDING, ELECTRIC PM, Visitor Center View Bldg","FM","PM","COMP",null,null,"71983","Visitor Center View Bldg","4100","4129","1",{"v":105230.93,"d":"$105,231"},{"v":1.2166666666666701,"d":"1.22"},{"v":25.66,"d":"$26"},0.75,{"v":20.96,"d":"$21"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":20.96,"d":"$21"}]
["12712031","PRESSURE WASH STEPS PM , Visitor Center View Bldg","FM","PM","COMP",null,null,"71983","Visitor Center View Bldg","4100","4129","1",{"v":105230.93,"d":"$105,231"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":3,"d":"3.00"},{"v":76.5,"d":"$77"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":76.5,"d":"$77"}]
["11159154","FY13 CABR Visitor Center View Building Custodial","FO","CU","APPR",null,null,"71983","Visitor Center View Bldg","4100","4129","1",{"v":105230.93,"d":"$105,231"},{"v":10,"d":"10.00"},{"v":250,"d":"$250"},143.75,{"v":3667.56,"d":"$3,668"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":3667.56,"d":"$3,668"}]
["11159501","FY13 CABR Visitor Center View Bldg Grounds","FO","GC","APPR",null,null,"71983","Visitor Center View Bldg","4100","4129","1",{"v":105230.93,"d":"$105,231"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":41.5,"d":"41.50"},{"v":1054.25,"d":"$1,054"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1054.25,"d":"$1,054"}]
["9993081","FY 13 Replace Signs in Park","FM","CR","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"}]
["11159533","FY13 CABR Bunker Inspections","FO","CU","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":10,"d":"10.00"},{"v":250,"d":"$250"},{"v":7,"d":"7.00"},{"v":182,"d":"$182"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":182,"d":"$182"}]
["11159308","FY13 CABR Staff Meetings","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":73,"d":"73.00"},{"v":2015.87,"d":"$2,016"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":2015.87,"d":"$2,016"}]
["11159335","FY13 CABR Training","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":170,"d":"170.00"},{"v":4638.9800000000005,"d":"$4,639"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":4638.9800000000005,"d":"$4,639"}]
["11159502","FY13 CABR Parts Pick Up","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},30.75,{"v":859.49,"d":"$859"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":859.49,"d":"$859"}]
["11159503","FY13 CABR Maximo Input","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},124.25,{"v":3257.27,"d":"$3,257"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":3257.27,"d":"$3,257"}]
["11159504","FY13 CABR Research for Project","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":60,"d":"60.00"},{"v":1677.02,"d":"$1,677"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1677.02,"d":"$1,677"}]
["11159505","FY13 CABR Gas Runs","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":6.5,"d":"6.50"},{"v":165.21,"d":"$165"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":165.21,"d":"$165"}]
["11159506","FY13 CABR Custodial Inventory and Ordering","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":7,"d":"7.00"},{"v":192.71,"d":"$193"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":192.71,"d":"$193"}]
["11159507","FY13 CABR HAZMAT Coordination","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":4,"d":"4.00"},{"v":100,"d":"$100"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":100,"d":"$100"}]
["11159509","FY13 CABR FLEET Coordination","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":45.5,"d":"45.50"},{"v":1219.88,"d":"$1,220"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1219.88,"d":"$1,220"}]
["11159512","FY13 CABR Contract Project Management WL","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1.5,"d":"1.50"},{"v":41.93,"d":"$42"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":41.93,"d":"$42"}]
["11159513","FY13 CABR Contract Project Management COM","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":192,"d":"192.00"},{"v":7956.31,"d":"$7,956"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":7956.31,"d":"$7,956"}]
["11159514","FY13 CABR WL Administration SWO","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":222.5,"d":"222.50"},{"v":6218.88,"d":"$6,219"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":6218.88,"d":"$6,219"}]
["11159515","FY13 CABR Supervision WL","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":67.5,"d":"67.50"},{"v":1886.63,"d":"$1,887"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1886.63,"d":"$1,887"}]
["11159534","CABR FMSS Annual Work Plan FY13","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":1582,"d":"1,582.00"},{"v":63835,"d":"$63,835"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":63835,"d":"$63,835"}]
["11159542","FY13 CABR Park Inspections","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":23.5,"d":"23.50"},{"v":638.3000000000001,"d":"$638"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":638.3000000000001,"d":"$638"}]
["11159571","FY13 Special Events SWO","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":9,"d":"9.00"},{"v":232,"d":"$232"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":232,"d":"$232"}]
["11159572","FY13 CABR Assist Other Divisions","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":31,"d":"31.00"},{"v":826.06,"d":"$826"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":826.06,"d":"$826"}]
["11159626","FY13 CABR Supervision METRO Workers","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":35,"d":"35.00"},{"v":978.25,"d":"$978"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":978.25,"d":"$978"}]
["11159627","FY13 CABR Safety Training","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":12,"d":"12.00"},{"v":320.74,"d":"$321"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":320.74,"d":"$321"}]
["11159628","FY13 CABR WL Ordering Park Supplies and Materials","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":33,"d":"33.00"},{"v":922.36,"d":"$922"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":922.36,"d":"$922"}]
["11159629","FY13 CABR  WL Work Planning and Management","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":68.5,"d":"68.50"},{"v":1914.57,"d":"$1,915"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":1914.57,"d":"$1,915"}]
["12264435","FY13 Paid Leave","FO","MG","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},811.25,{"v":21258.83,"d":"$21,259"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":21258.83,"d":"$21,259"}]
["11159336","FY13 CABR Recycling","FO","RC","APPR",null,null,"CABR","Cabrillo National Monument","0000",null,null,{"v":0,"d":"$0"},{"v":0,"d":"0.00"},{"v":0,"d":"$0"},{"v":35.5,"d":"35.50"},{"v":903.79,"d":"$904"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":0,"d":"$0"},{"v":903.79,"d":"$904"}]